## Sheet1
Ryan's-Play Project |  | Android |  | iOS
Date | Works Assigned by client | Issues taken up by MK | Issues taken up by Sheshank | Issues taken up by Vinodh | Issues taken up by Vivek
26th May | Try to solve the 21 issues and update the status in Jira. Priority: 1.Score Calculations. 2.Predictions with Enable and Disable. 3.Crashanalytics. 4.Code commit to GitHub. | Try to solve the 21 issues and update the status in Jira. Priority: 3.Crashanalytics. 4.Code commit to GitHub. | Try to solve the 21 issues and update the status in Jira. Priority: 1.Score Calculations. 2.Predictions with Enable and Disable. | 1. Score Caluclation. 2. Predicitions 3.Crashanalytics. 4.Code commit to GitHub. | 1. Solve the pending jira's: RP6,RP7,RP11,RP12,RP19
27th May | 1.Score Calculations(Verification). 2.Predictions with Enable and Disable(Verification). 3.Crashanalytics. 4.Solve the pending jira's RP3, RP4, RP5, RP9, RP16(Android) RP3, RP4, RP5, RP9, RP14, RP18, RP20(iOS). 5.Verify the Jiras which are fixed. | 1. Crashlytics 2. Score calculation(Verfication) 3.jira's Rp3, Rp4, Rp5, Rp9 4. verify the fixed jira's | 1. Predictions with enable and disable(Verification). 2. jira's Rp16 3. verify the fixed jira's | 1.Score Calculations(Verification). 2.Predictions with Enable and Disable(Verification). 3.Crashanalytics. 4. Solve the pending jira's: RP3,RP14,RP18. | 1. Solve the pending jira's: RP20.